The Seedling Initiative:

Cultivating Automation to Harvest Operational Efficiency and Cost Savings

Kate Herrick

Capella University

IT-FPX 4998: Capstone II

Site Supervisor: Angela Baughman

November 11, 2025

Organizational Introduction

Greenfield Financial operates as a Farm Credit System Agricultural Credit Association (ACA), serving client-shareholders across multiple states. As a financial cooperative, the organization’s mission relies on deep relationships and maintaining the fiscal health of its agricultural clients. A hallmark of the ACAs operating within the Farm Credit System is that they function akin to a consumer credit union, paying dividends annually to shareholder clients as a percentage of client interest payments. Greenfield leverages this operational feature as a core aspect of its mission, “Enriching agriculture and rural America.”

A critical element of Greenfield’s credit operations includes the annual submission of detailed balance sheets (assets, liabilities, income, and expenses) used for portfolio analysis, client evaluation, and regulatory reporting to the Farm Credit Administration (FCA). All clients with non-residential credit balances are required to submit balance sheets prior to the end of the reporting year on December 31. Greenfield mails pre-printed forms to all such clients, who complete them by hand and return them either in person or via US Mail. During the entire month of January, Greenfield marshals internal resources to undertake the laborious task of hand-keying balance sheet data. Employees are required to work nights and weekends, resulting in a substantial burden and a degradation in morale. In addition, the current process presents a critical risk and efficiency bottleneck:

Manual Data Entry Risk: The manual process of hand-keying data introduces significant risk of human error, potentially compromising data integrity for financial evaluations.

Operational Bottleneck: The resource demand during January's annual reporting cycle drains highly skilled staff from strategic work (relationship management, analysis) into tedious, low-value data transcription.

Compliance Vulnerability: The paper-based process increases the surface area for physical data loss, violating modern data security expectations for sensitive financial information.

The Seedling project is chartered to transform this manual process into a secure, end-to-end digital data integration pipeline.

Site Supervisor Introduction

The site supervisor for this project is Angela Baughman, the Principal Product Manager for several Greenfield credit origination systems. Prior to her current role, Angela served as product owner for the client portal that will be leveraged by the Seedling project and as an IT development manager. Angela has been with Greenfield for seven years. Her experience as the product owner of Greenfield’s client portal enabled her to transition into the leadership of an IT team charged with the continual improvement of the platform before later moving back into product management. She has line of sight into and influence with most of the organizations that have a vested interest in this project’s outcomes and is familiar with the IT processes and resources required to build, test, and deploy a complex solution. Angela’s external experience with significantly larger organizations, pre-dating her employment with Greenfield, provides her with the foundational understanding for large-scale process improvement initiatives with multiple beneficiaries.

Identification of the problem, issue, or improvement area selected

The Seedling project is a strategic response to the toll that the manual data entry labor necessitated by Greenfield’s existing processes takes on its staff and budget. The cost of hand-keying balance sheet data every January exceeds $3 million and requires employees to work nights and weekends for the final three weeks of every January. Because Greenfield’s employees are the key to the formation and management of the intimate business partnerships that the organization’s clients expect, it is a strategic imperative to protect staff well-being. Additionally, Greenfield would be positioned to refund a greater percentage of interest revenue to clients if the cost of labor associated with balance sheet data entry could be reduced, directly contributing to fulfilling its mission. This project is chartered to eliminate manual data entry of client balance sheets by implementing a fully automated, secure data flow from client submission through all core enterprise systems.

SWOT Analysis: An Assessment of Greenfield’s Marketing, Information Technology, and Organizational State

This SWOT analysis provides an assessment of the internal and external factors influencing the success of a planned technical project at Greenfield Financial. The project under consideration, an end-to-end solution for client input of balance sheet data via the organization’s client portal that includes data integration through a pair of downstream systems, would enable Greenfield to realize substantial labor cost savings while releasing vital staff resources to carry out higher-value work in support of Greenfield’s mission.

The most significant finding of this analysis is that a clear imperative exists to deprecate expensive, labor-intensive processes in favor of client self-service and data integration. In so doing, the organization stands to realize significant cost savings while improving staff morale and data integrity. However, the project's success is at risk due to resource constraints on key subject matter expert resources, who are constantly in demand for similar efforts. Additionally, the project is wholly dependent on adoption by Greenfield’s clients, most of whom do not currently interact with the organization’s client portal.

The project is not only technically feasible, but Greenfield already has the technical infrastructure to complete the project with no expenditures except labor costs. However, its viability requires that organizational leadership market the client portal successfully in order to generate the submissions necessary to leverage the resulting automation.

## Detailed SWOT Quadrant Analysis

| Category | Assessment | Focus | Key Findings |
| --- | --- | --- | --- |
| Strengths | Helpful | Internal | Organizational stability, financial profitability, and a robust technical foundation. The IT team is proficient and the organization is profitable. Similar projects involving data integration have been completed successfully and Greenfield is well-positioned to financially support the endeavor. |
| Weaknesses | Harmful | Internal | Adoption of client portal functionality has been slow to materialize since deployment. Although the client portal has existed for several years, its functionality has been constrained to read-only information display and has had limited utility for its intended user base. |
| Opportunities | Helpful | External | Clear opportunity to enhance client experience, thereby establishing market differentiation. Most farm credit ACAs rely heavily on manual processes by virtue of their size, which tends to be small. Greenfield is among the largest ACAs in the United States and has the opportunity to improve its standing by adopting friction-free services that improve client loyalty. |
| Threats | Harmful | External | Regulatory risk in a highly-regulated sector. Although data governance requirements as mandated by Greenfield’s regulatory bodies have been relatively stable in the preceding years, there remains the risk that changes to such requirements during or after implementation may require substantial refactoring or abandonment of the project altogether. |

## Discussion Points and Strategic Action Basis

This section outlines the areas that will be addressed with the site supervisor to ensure the project aligns with organizational goals and mitigates known risks.

An unused path: improving client portal adoption rates

The most substantial internal risk is the lack of client adoption of the functionality available in the client portal. Historically, the portal has only provided account summary data such as amortization schedules, payment and balance information, and disbursement history. The proposed solution is reliant on client use of the portal, including not only by clients already using the platform, but by the much larger group of clients who have never enrolled in the portal. Without improved adoption and utilization, the organization runs the risk of building a solution that will go unused as clients revert to the manual process.

- Discussion Point: How can the organization effectively market the portal to its client base to ensure that utilization rates not only justify the development and implementation cost but also lead to real cost savings and reduced manual labor? What adoption rate would justify the expense of the project while enabling the realization of tangible benefits?

Subject Matter expertise: The bottleneck

A consistent obstacle in a number of major initiatives at Greenfield emanates from the constraints on the availability of much-needed subject matter experts. The Seedling project is no exception. Greenfield employees with the knowledge to manage complex data integration, particularly relative to data mapping and validation, are in constant demand as the organization expands use of microservices architecture to automate processes and improve reporting. Given the limitations on such resources, an imperative must be established for the Seedling project that establishes its priority over other comparable projects and that protects SME resources from reallocation/overallocation while they are needed for the critical path elements of Seedling.

- Discussion Point: In light of the challenge of client adoption rates, how can a case be made to an executive sponsor that subject matter experts should be dedicated to Seedling for its duration and should be protected from other engagements that lack the risk of underutilization?

Critical Threats Requiring Mitigation

| Threat Detail | Recommended Mitigation Strategy |
| --- | --- |
| Low Client Portal Adoption and Utilization Rates | The project will need to define time-bound Key Performance Indicators (KPIs) that establish thresholds for adoption and utilization required to meet the efficiency and cost savings targets set by leadership and owned by the Business Owner. |
| Subject Matter Expert Bottleneck | The Business Owner will need to establish a business case with executive leadership that asserts ROI predicated on client adoption rate in a bid to justify the dedication and protection of SME resources for the data integration needs of the project. |

Environmental Scan for Project Seedling

This Environmental Scan reviews external factors that impact the organization and the proposed solution. The analysis formalizes the Opportunities (O) and Threats (T) identified in the SWOT, providing context for implementation of a solution that is technically viable and compliant with data governance requirements. The proposed IT solution for the development of an end-to-end solution for data ingestion and integration must address those risks and capitalize on the opportunities presented by the external environment.

- Regulatory And Compliance Outlook

The most significant external threat to the project’s success is the potential for the data governance requirements of Greenfield’s regulatory bodies to change during the project or after its completion. While the regulatory environment relative to data governance has been stable for some time, the prospect of changes must be factored into the risks to be considered.

| Focus Area | Key External Factors | Project Impact & Risk |
| --- | --- | --- |
| Mandated Changes to Uniform Data Standards | The Farm Credit Association dictates the content and calculation methodology of all data submitted to Greenfield’s wholesale lender, Agribank. | Low Risk. Changes in how debt or asset ratios are calculated, inclusion or exclusion of new balance sheet line items outside of GAAP accounting norms, or other updates could impact either work in flight, delaying the project, or require post-deployment refactoring. |
| Increased Audit Trail Requirements | The Farm Credit Association serves as Greenfield’s auditor, ensuring the integrity of both its portfolio analysis data and its non-public personal information (NPPI). | Low Risk. The FCA has the potential to require stricter audit trail data collection for client-submitted balance sheet data. Because the data is not accompanied by a signature on submission, the FCA may require that each line item entry be stamped with date and time of entry, along with a history of updates to the line item entries prior to submission. This would require storage of transactional data that, in turn, would necessitate development of additional data repositories. |

2. Market and Competitive Forces

This analysis confirms the market need for improved automations while acknowledging the intensifying competition in the agricultural lending and financial services industry.

| Focus Area | Key External Factors | Project Opportunity/Threat |
| --- | --- | --- |
| Shareholder Demand for Self-Service | Despite mythology to the contrary, agricultural businesses are highly technical entities that demand modern, efficient digital tools to facilitate financial transactions. | Opportunity. Clients in the agricultural sector are no different than clients in other lines of business. While they may have access to online banking, lending, and other financial services in their personal lives, they are limited in the access they have to similar digital solutions in their business lives. Development of a means of online balance sheet submission has the potential to serve as a foundational first step in transforming the digital experience of Greenfield’s shareholder clients, improving customer experience and client retention. |
| Operational Cost Efficiency | In any lending environment, operational efficiency is key to maintaining competitive interest rates and profitability. | Threat. Greenfield’s clients are also shareholders in the organization. As labor costs increase, clients will see reductions in annual interest refund payments and potentially higher interest rates, making Greenfield less competitive in the agricultural financial services space. Development of automated processes that reduce manual work will also reduce expenses, improving Greenfield’s own balance sheet and enabling it to meet its mission to enrich agriculture and rural America. |

- Technological and Platform Trends

This analysis reviews trends in technology and platform development that inform the project and its dependencies.

| Focus Area | Key External Factors | Project Opportunity/Threat |
| --- | --- | --- |
| Data Economy and Source Systems | A market trend toward using data integrations across enterprise systems for real-time information retention, transformation, and storage. | Opportunity. Greenfield already possesses the means to integrate data across enterprise platforms, both those that serve as the organization’s Single Source of Truth (SSOT) and those that serve as wholesale lender AgriBank’s SSOT. Those means merely require modification in order to create the data pipeline for balance sheet information, reducing the organization’s level of effort while bringing Greenfield’s technology platforms into alignment with market trends. |
| Emergence of Expert Systems in Data Analysis | Financial services organizations are well-known for their use of expert systems that mimic artificial intelligence by serving as decision engines or predictive models. | Opportunity. As Greenfield leverages both API and ETL processes to integrate and transform financial data, it opens the door to the development of expert systems that leverage native data for use in portfolio analysis, default prediction, valuation modeling, and other AgFinTech initiatives. |

Environmental Scan Conclusion and Next Steps

The Environmental Scan confirms that market demand exists for the proposed solution, but the low adoption rate of the existing client portal and the availability of subject matter experts both pose the greatest threats to the project. Greenfield’s IT team cannot manage these threats via development. Prior to project initiation, it is incumbent on the business to more aggressively market client enrollment in the existing portal and to establish benchmarks for utilization that justify the cost of the Seedling project by quantifying the cost savings to be realized if those KPIs are met. Additionally, the business will need to successfully defend SME allocation through justification of the project by meeting the KPIs that enable the forecast of anticipated expense savings from the project’s implementation.

An analysis of the intersection between a SWOT and the development of a project charter

A project charter directly translates the findings of a SWOT into the scope, objectives, and governance principles that will guide the project. Specifically, the SWOT’s identification of opportunities establishes the rationale for the project and its expected outcomes, while the weaknesses identified in the SWOT inform the project’s assumptions, constraints, and risks. In the case of the proposed project, implementation of a solution to labor-intensive manual processes and the quantification of the solution’s impact on expenses associated with said processes in the form of tangible savings provide a compelling business case. In addition, the SWOT analysis identified the biggest threat to the project, which is the low utilization of the existing client portal, which will serve as the ingress point for balance sheet data following solution implementation. The SWOT therefore mandates that the business establish a case that provides for plans to improve portal utilization rates and that establishes utilization KPIs that, when met, would both justify the expense of the project and enable forecasting of cost savings resulting from online balance sheet submissions. The role of the business in justifying the initiative is outside of the scope of the project, but it assures that the project is a viable effort that will have executive support over its lifespan.

Development of a project charter

As a senior business analyst with over 25 years of industry experience, I’ve written a number of project charters over my career, a skill that has been greatly enhanced by my coursework in the last eight months. The project being explored during this Capstone was undertaken by the organization in the spring of 2020 and completed approximately three months later. However, the project was limited in scope to the development of the user experience in the client portal without the data integration efforts described herein. As a result, I’ll be developing the project charter in retrospect with particular attention to the value added by the integration of a data pipeline originating on submission and passing through Greenfield’s Salesforce instance en route to AgriBank’s core banking systems.

The project scope will be defined to include the development of a complex balance sheet tool within the existing client portal that enables the input of income, expenses, assets, and liabilities that are categorized to align with an agricultural operation. Clients will have the ability to input assets such as farm equipment and vehicles, liabilities such as revolving and operating lines of credit, real estate loans, and similar credit facilities, and other molecular data that represents the client’s financial position and health. Because the client portal was built leveraging Salesforce’s native Experience Builder functionality, the data can be passed into a custom Salesforce object without requiring API development. Two existing ETL batch jobs will require modification, one to include balance sheet data stored in the custom object to a series of on-premises SQL databases that are updated nightly with Salesforce data extracts, and another to transmit the data from the databases to AgriBank’s core banking system.

Project Charter

| Project Name | “Seedling” |
| --- | --- |
| Department | - Client Financial Services - Portfolio Accounting - Information Technology |
| Focus Area | - Client Experience - Process Improvement |
| Product/Process | Digital Client Balance Sheet Submission with Data Integration |
| Prepared By | Kate Herrick, Project Manager |

Project Charter Version Control

| Version | Date | Author | Change Description |
| --- | --- | --- | --- |
| 1.0 | November 11, 2025 | K. Herrick | Initial draft |

- Project Charter Purpose

The purpose of this project is to successfully implement a client-facing balance sheet tool on Greenfield Financial’s existing client portal website. The core goal is to remediate manual data entry processes by enabling clients to self-serve via the portal and to transmit the resulting data through Greenfield’s core systems to its final resting place with Greenfield’s wholesale lender, AgriBank. In so doing, the project endeavors to reduce tedious manual work that negatively affects employee work/life balance while simultaneously reducing expenses, ensuring data integrity, and improving client experience. This project is chartered on the basis of the establishment of client portal enrollment and engagement KPIs by the business that, when met, justify the project’s cost and define its tangible objectives.

- Project Executive Summary

This charter outlines the plan to build a balance sheet data ingress solution suitable for implementation on Greenfield’s externally-facing portal website that allows its clients to input itemized balance sheet data specific to agricultural business practices and that leverages a series of integrations to transmit the resulting data through Greenfield’s systems. This is a strategic imperative designed to mitigate current costs in excess of $3 million per year while improving employee experience and retention. The project is structured to deliver the proposed solution, but requires that dependencies identified in the SWOT analysis upstream of the project be resolved before initiation to proceed:

- The requirement that KPIs for client portal enrollment and utilization be developed and met as a means of both forecasting labor expense savings and justifying the cost of the project.

- The need for business owners to obtain executive sponsorship for the project that allocates and defends subject matter expert resources crucial to data mapping and validation during ETL job modification.

Project success is defined solely by technical delivery, but is entirely dependent on the business establishing and meeting KPIs in advance of the project that justify it.

- Business Needs

Drivers for this project include:

| Impetus | Rationale |
| --- | --- |
| Improve Employee Experience | Greenfield’s employees are asked on an annual basis to undertake tedious manual work that impairs work/life balance. The successful implementation of this project would mitigate employee dissatisfaction, which would in turn improve the retention that is a cornerstone of Greenfield’s operations. |
| Reduce Labor Costs | Greenfield spends over $3 million per year in labor expenses in association with manual balance sheet data entry. Reducing this expense would enable Greenfield to offer lower interest rates and larger annual interest refunds to its clients, improving client retention and goodwill. |
| Competitive Differentiation | The project poses an opportunity to build on Greenfield’s data automation initiatives and would be the first data pipeline that moves client-furnished information from an ingress point through all Greenfield systems to its resting place at AgriBank. |

- Business Case

The project is a strategic necessity driven by the triple imperatives of cost efficiency, client satisfaction, and employee morale. By replacing antiquated, paper-based balance sheet submissions and the associated manual data entry with a digital ingress point for balance sheet data and a full data pipeline through Greenfield’s systems, the organization is anticipated to reduce the current $3 million expense associated with balance sheet processing to $1.5 million per year, against a projected project cost of $112,000. The savings realization was forecast as a result of established KPIs that mandated a client portal enrollment rate of 75% of the client base and a portal utilization rate of 60%. Having met these performance metrics, the business asserts that annual cost savings of $1.5 million will be realized as a result of this project. In addition, this transition simultaneously delivers a significant upgrade to the client experience, delivering functionality on the client portal that is genuinely useful by moving beyond read-only transactional data presentation. The project is also anticipated to dramatically improve employee morale, reducing or eliminating the need for tedious, error-prone drudge work that interferes with evening and weekend personal pursuits and obligations. All of these benefits speak directly to Greenfield’s mission to foster the economic well-being of the agricultural sector, since cost savings will be returned to client-shareholders via lower costs and higher interest refunds, and retained employees will be positioned to maintain and invest in client relationships.

- Project Requirements

- Portal Modification:  The existing client portal will be modified to include balance sheet functionality that permits clients to input assets, liabilities, income, and expenses in a line item format that adheres to accounting practices of agricultural business operations and that allows the client to submit the collective entries as a final version.

- Date Ingress: A new Salesforce custom object will be developed that will store the detailed data input by the client.

- Data Storage: Greenfield’s existing on-premises SQL databases must be modified to store the data in the new Salesforce custom object.

- Data Integration: An existing ETL job must be modified to include data in the new custom Salesforce object when transferring client data to Greenfield’s on-premises SQL databases on a nightly basis.

- Data Integration: An existing ETL job must be modified to include balance sheet data stored in the on-premises SQL databases for transmission to AgriBank’s core banking systems.

- Data Validation: Extensive validation of data at rest and in transit must be performed at each step in the transmission process.

- Configuration Management Requirements

Configuration management for this project will focus on the following key assets:

- Project Documentation: All documents (Charter, Requirements, Calculation Use Cases, and ETL functional specification artifacts) will be stored in Greenfield’s centralized, version-controlled project repository.

- Code: All custom code will be managed in Greenfield’s IT source control system.

- Change Management and Control: Any request for changes to the project scope, schedule, budget, or data mapping logic itself must be formally submitted, reviewed by the project’s Change Control Board (CCB).

- Project Boundaries

The scope of this project is limited to:

- Development, testing, and deployment of the balance sheet functionality in the client portal and its associated calculation logic.

- Development, testing, and deployment of the new custom Salesforce object responsible for storing data ingested via the portal.

- Development, testing, and deployment of the updated ETL integration infrastructure between systems.

The project does not include:

- Integration with Greenfield’s document management system for storage of data in document format.

- Any changes to the core business logic or financial data within Greenfield’s core systems outside of balance sheet data.

- Milestones

| Milestone | Target Completion Date |
| --- | --- |
| Project Charter Approval | January 2026 |
| Design Completion | February 2026 |
| Detailed Requirements Completion | March 2026 |
| Balance Sheet Calculation Development | March 2026 |
| Client Portal Interface Development Completion | May 2026 |
| ETL Job Modification Completion | July 2026 |
| System Testing and UAT | August 2026 |
| Production Launch | September 2026 |
| Project Closure and Post-Implementation Review | September 2026 |

- Work Breakdown Structure

1.0 Initiation and Planning

1.1	Project Charter Approval

1.2	Team Kickoff and Resource Allocation

2.0 Detailed Analysis

2.1	High-Fidelity User Interface Designs

2.2	Detailed Requirements Completion (Functional and Technical Specifications)

2.3	Calculation Logic Definition

2.4	Data Mapping and ETL Specification Completion

2.3	Test Plan Development

3.0 Execution

3.1	User Interface Development

3.2	Salesforce Custom Object Development

3.3	ETL Job Modification Build

4.0 Testing

4.1	Unit Testing

4.2	Integration Testing

4.3	End-to-End Testing

4.4	User Acceptance Testing (UAT)

5.0 Deployment and Closure

5.1	Production Deployment

5.2	End User Training

5.3	Post-Implementation Review & Lessons Learned

- Project Stakeholders

| Stakeholder | Organizational Role | Vested Interest/Impact |
| --- | --- | --- |
| Kara Long | Executive Sponsor/Client Financial Services Director | Final budget authoring and success metric accountability |
| Angela Baughman | Site Supervisor/Product Manager | Product manager and project sponsor |
| Angie Anderson | Business Analyst | Defines user interface requirements, calculation logic, data mapping requirements, and ETL specifications |
| Joel McCabe | Technical Lead | Leads API and user interface development |
| Mike Black | Training and Process Lead | Coordinates and trains internal resources |

- High Level Budget

| Project Expense | Estimated Cost | Rationale |
| --- | --- | --- |
| Labor - Business Analysis - IT Development - Testing | $112,000 | Nine-month, four-person team development effort. |
| Total Estimated Cost | $112,000 | Required investment to achieve the estimated $1.5M annual cost savings. |

- Project Conditions

- Project Assumptions

- The funding and dedicated IT resources necessary for the entire development effort will be maintained and protected from being engaged for other priorities.

- The data integration team will have resources available on a timely basis to guide data mapping efforts if needed.

- Subject matter experts at AgriBank will be available to support mapping tasks and to validate endpoint data ingress.

- Project Risks

Risk 1:

Subject Matter Expert Availability: Both internal and external subject matter experts (SMEs) needed to ensure proper data mapping and testing/validation have enormous constraints on their time due to the number of data integrations being implemented by Greenfield. If they are not available for this project, the timeline and scope will be at risk.

Mitigation: As a precursor to the project, the business was obligated to seek executive sponsorship that included SME resource allocation and defense. The resources remain at risk in the event of production issues or other critical business problems, but the risk is mitigated by the sponsor’s influence.

Risk 2:

Regulatory Updates: While minimal, a risk exists relative to changes to regulatory and compliance requirements concerning balance sheet calculation logic, data elements, or aggregation of data that could impact both the user interface and its resulting data.

Mitigation: The project manager will establish regular communications with Greenfield’s internal compliance officer to evaluate project requirements and deliverables against the current regulatory landscape and will escalate any deltas to the executive and project sponsor immediately.

Risk 3:

Data Integration Complexity: The ETL integration may prove significantly more complex or costly than estimated, impacting the timeline and budget.

Mitigation: The team will begin analysis early in the project leveraging existing ETL functional specifications in a bid to avoid delays should the ETL job updates be more complicated than anticipated.

- Project Constraints

- Timeline: The solution must be deployed by September 2026 so that any post-deployment refactoring or enhancements can be launched before balance sheet input begins in December 2026.

- Scope: Use of the balance sheets is constrained to clients with open, active agricultural credit accounts.

- Platform: The user interface will be implemented on the existing Salesforce-based client portal leveraging a custom Salesforce object. Data transmission will leverage existing ETL batch jobs and the existing on-premises SQL databases.

- Acceptance Criteria

The project will be considered complete and successful when the following criteria are met:

- The new balance sheet functionality successfully passes client inputs to the new custom object in Salesforce.

- The existing ETL job that sends client data on a nightly basis to the on-premises SQL databases will successfully include balance sheet data originating in the new custom Salesforce object.

- The existing ETL job that sends client data on a nightly basis to AgriBank’s core banking system will successfully include the balance sheet from the on-premises SQL databases.

- The full end-to-end integration demonstrates 100% accuracy for all tested calculation use cases.

- All internal Salesforce and external AgriBank resources are fully trained and able to access and evaluate balance sheet data in their respective systems.

- Approval Requirements

Project approval will be granted when the Project Charter is signed by the designated approvers. Subsequent approvals required during the project lifecycle include:

- Approval of detailed requirements and design documents.

- Mandatory approval during the Legal/Compliance Gateway.

- Approval of the test plan and successful sign-off on User Acceptance Testing (UAT).

- Approval from the Executive Sponsor to proceed with production deployment.

- Approvals

| Action | Name | Role | Date |
| --- | --- | --- | --- |
| Prepared By | Kate Herrick | Project Manager | November 11, 2025 |
| Approved By | Kara Long | Executive Sponsor/Client Financial Services Director |  |
| Approved By | Angela Baughman | Site Supervisor/Product Manager |  |
| Approved By | Angie Anderson | Business Analyst |  |
| Approved By | Joel McCabe | Technical Lead |  |